## Sheet1
SWWA FYSPRT Workplan January 2023 through December 2024- Updated April 2023
Priority | Goal | Action Items | Owner | Status | Target Completion
Develop youth advocates and increase focus on youth-driven agendas. | FYSPRT youth leaders are identified and developed | Host at least 6 Youth Advocacy and Empowerment Meetings, a space for youth to share their experiences. | Tri-Lead |  | 2024-12-31
|  | Provide financial support to Adulting 101 meetings to encourage youth participation. | Convener |  | 2024-12-31
|  | Community Spotlight of 14 youth in monthly newsletter with opportunity and encouragement to present at the monthly regional FYSPRT meetings. | Convener |  | 2024-12-31
FYSPRT represents the experience of youth and families navigating and interacting within the systems of Clark and Skamania Counties to aid in system development. | At least 51% youth and family membership attendance at regional meetings. | Develop timeline and implementation plan for meeting format preference, including equipment that will be needed and securing space if necessary. | Convener |  | 2023-06-30
|  | Determine and implement approaches that expand recruitment and engagement of youth and families, focusing on both traditional and non-traditional providers and schools. | Tri-Lead |  | 2024-12-31
|  | Poll members of FYSPRT and YAE to determine perferred method of meeting format. | Convener |  | 2023-03-31
|  | Develop process to allow for membership growth without encouraging virtual scammers. | Tri-Lead |  | 2023-03-31
Build FYSPRT as a platform to use for awareness, outreach, education and a forum to present topics that are impactful to the youth and family within the community. | Relevant community members and system partners are engaged in FYSPRT. | Identify and participate in community resource events, minimum four annually. | Tri-Lead |  | 2024-12-31
|  | Plan and facilitate at least one annual event that aids in awareness, outreach, and education in support of the FYSPRT mission. | Tri-Lead |  | 2024-12-31
|  | Encourage block grant recipients that provide services to youth to participate regularly in monthly regional meetings. | Convener |  | 2023-09-30
|  | Include in the monthly Newsletter including free resources, resources to improve wellbeing and resources for those in BIPOC and/ or Asian & Pacific Islander communities. | Convener |  | 2024-12-31
Increase visibility of SW WA FYSPRT through networking, outreach and partnering with Schools and other system partners within our region. | Increase regular meeting attendance by 4 new attendees . | Distribute FYSPRT brochures within community, including Spanish-speaking. | Members |  | 2024-12-31
|  | Identify community activities to encourage utilization of the SWWA FYSPRT Facebook page and Instagram account. | Tri-Lead |  | 2024-12-31
|  | Present at System Partner meetings twice during the year about what FYSPRT is, how it is beneficial and why someone would want to attend. | Tri-Lead |  | 2024-12-31
|  | Increase reminders and visibility of monthly FYSPRT meetings through the distribution of a monthly newsletter. | Convener |  | 2024-12-31
Maintain and improve FYSPRT operations according to regional needs and statewide manual. | Ensure SWWA FYSPRT information is timely, accessible and accurate. | Conduct annual needs assessment to update community priorities and refresh strategic workplan. | Convener |  | 2023-10-31
|  | Maintain and improve FYSPRT website with timely updates. | Convener |  | On-going
|  | Participate in quarterly statewide FYSPRT meetings. | Tri-Lead |  | 2024-12-31
|  | Respond to statewide FYSPRT requests for regional input. | Tri-Lead |  | 2024-12-31